## Sheet1
HOPS upgrade: Tracking of 2/4/2021 review comments & responses
Originated by JFS 24 Jan 2021
Requirements Document
Specification Document
Schedule
# | Initiator | Title | Category | Description | Responder | Response &/or action | Actions /Comments | Response Date | Additional Comments | Coverage and Test Plan
1 | Shep | MSRI scope | Requirements Document | First sentence in intro says MSRI is launched by EHT, which is not correct. The MSRI is a new project, and the ngEHT is separate from the EHT. Better: "The next-generation EHT (ngEHT) is a significant and transformative extension of the EHT, the design of which is funded by a Mid-scale Research Infrastructure (MSRI) award from the NSF. " Or something like that. | Dan H. | Fixed. |  | 2021-03-02
2 | Shep | requirements | Requirements Document | Section 1 says that 128Gb/s 'has been mentioned', but it is more likely that we will settle on 256Gb/s (if 2-bit; more if higher bit depth, and one could consider over-sampling too). | JB | replaced with: (up to 256 Gbps if sampled at 2-bits over four dual-polarization, 4 GHz bands) |  | 2021-03-02
3 | Shep | requirements (section 2.4) | Requirements Document | In section 2.4 there are several post-processing routines that will be maintained or ported to HOPS4. Are these consistent with the overall ngEHT data processing architecture? Are these functions that will exist in HOPS, or are they covered outside of HOPS for the ngEHT? | VP | If the post-processing routines in HOPS4 will be consistent with the ngEHT data processing architecture is still TBD. This is contingent on on the HOPS4 team being provided this information from the ngEHT customer. |  | 2021-03-02
4 | Garret | Design sensitivity to future use case changes | Requirements Document | Assumption that general use cases for HOPS software package are expected to follow the existing use model… how sensitive is the design to changes in possible use cases? In other words, since we haven't finalized the use cases for the ngEHT, how much of a risk do we have that we could require re-design based on conceivable operational deviations from the current EHT operations? |  | Much of the underlying library code should still be re-usable if there are use-case changes that only affect the features needed in post-processing applications, so the risk in that regard is somewhat low. |  | 2021-03-02
5 | Garret | Schedule margin to incur additional risk to re-design | Requirements Document | Related to the above question, at what point in the schedule do we start to incur additional risk for re-design because the use cases and high level requirements haven't been finalized? | JB, DH | Schedule risks incurred from re-definition of requirements will be non-zero starting now and will grow as the project becomes more mature. The magnitude of the risk depends, of course, on the nature of the change. We expect to have a minimally-viable fringe fitter by ~March 2022, so adjustments to base components are much easier before this date. |  | 2021-03-02
6 | Kari | Automake v. CMAKE | Specification Document | (Suggestion, not requirement). I'd say just make a choice on this one. Putting too much effort into making the "perfect" decision isn't going to pay back much (though my vote is CMAKE). | VP | My understanding is we are migrating to cmake. We still need to support and ensure that the necessary functionality of automake is replicated in the new cmake compile/build process (currently not all automake functionality is yet replicated with the cmake system). |  | 2021-03-02
7 | Kari | Data containers | Specification Document | How are you decoupling the in-memory data layout? Using a tool like CEREAL? | JB | To keep the I/O as efficient as possible, the initial plan for (at least) binary data is to write stream operators for each data container type. If a wider variety of formats (JSON/XML) is desired for inspection, adopting a header-only library like CEREAL is a good possible option. |  | 2021-03-02
8 | Kari | Data operator | Specification Document | Possibly want to use smart pointers instead of raw pointers? Also const for inputs to protect for multi-threading. | JB | In this case there is no dispute over object ownership (the operators do not allocate/destroy the data containers, only modify them) so smart pointers are not strictly necessary. If we do find them to be useful, then the implementation can be changed without any external affects. Imposing const on the inputs may be a good idea and this can easily be changed if it is all data operators can be guaranted not to need to modify the inputs. However, it may in some cases be advantageous not to impose this restriction, as in some computing models (e.g. OpenCL) some logically non-const operations may be need (even if the data is unaffected); for example, copying and caching a buffer to a device. |  | 2021-03-02
9 | Garret | A-4 | Requirements Document | A-4 should split these requirements 1) test functionality with at least 128 channels, 2) shall not impose a limit on the number of channels | JB | Splitting will change the requirements numbering, and unfortunately other documents aren't robust to chnages to numbering, this has been reworded. |  | 2021-03-02
10 | Garret | P-7 | Requirements Document | P-7 should there be a limit on the impact on runtime? I.e. do we care about keeping that impact below a certain threshold? | JB | There is no concern for impact on runtime in this requirment, as this is focused on usability of the software while testing, rather than optimization for production. For example, we want to make it possible to test the functionality of the software on systems where the end-user may not have permission to install all of the dependencies. In that case it is important that they have a means of compiling/running and testing the functionality of the software before they concern themselves with optimizing its performance. If it is found the performance suffers beyond what the user desires when using a particular fall back option, the solution is simply to adopt the optimizing 3rd party library. |  | 2021-03-02
11 | Garret | Runtime requirement | Requirements Document | In general, is there any overall requirement on total runtime? | JB, VP | Any requirement on this would need to specify the exact data-set, software application and procedure to be applied in order for this to be testable. It's not immediately clear to me what an appropriate test(s) would be, and whether it would neccessarily be representative of eventual ngEHT use. Currently the desire is to have runtimes that are are comparable with HOPS3 or otherwise an improvement over HOPS3 runtimes. |  | 2021-03-02
12 | Garret | A-10 | Requirements Document | A-10 should we specify what is meant by 'every application'? Is it truly every application? | JB | This applies to every application which will be provided to the user in the HOPS4 software package. |  | 2021-03-02
13 | Garret | Requirement rationale | Requirements Document | In general, all requirements documents should have rationale for every requirement. | VP | Fixed. |  | 2021-03-02
14 | Garret | A-16 | Requirements Document | A-16 should define what 'valid' means wrt 'valid A-list files' | JB | alist defines a 'version 6' format, specifying the data type of each column, is valid with respect to reading/writing for this version (6). |  | 2021-03-02
15 | Garret | A-17 | Requirements Document | A-17 should define what 'valid' means wrt 'valid ASCII text representations of columns of data from an A-list of version 6' | VP | Fixed. |  | 2021-03-02
16 | Garret | Preserving functionality of HOPS3 | Requirements Document | For any requirement that calls for preserving functionality of HOPS3, how do we ensure that full functionality is ported over and tested, and not just some portion of that functionality? | VP | The requirements artifact contains all of the functionality from HOPS 3 that will be ported over to HOPS4. A test artifact is planned to be created by the HOPS4 team that shall contain all the necessary use cases and experiments to be tested. The results of these tests will be compared against the equivalent results from HOPS3 with the understanding that HOPS3 is the test oracle. |  | 2021-03-02
17 | Garret | P-25 / P-26 | Requirements Document | P-25 and P-26 since these are 'shoulds' does that mean they're nice-to-haves? | DH | These "shoulds" shall be changed to "shalls". Fixed. |  | 2021-03-02
18 | Garret | P-27 | Requirements Document | P-27 "interactive visualization tools" is very broad. How do we ensure this requirement captures what the customer wants? | DH | It's purposefully vague, I think; this is a broad topic and we don't have the resources to support every desire. It would be helpful for the EHT to provide specific applications they'd like to see so we can prioritize development. |  | 2021-03-02
19 | Garret | D-28 | Requirements Document | D-28 not worded as a requirement. Unclear from the comment below it why this is a requirement. | DH,JB | This is a requirement (python-based control file for fourfit), and has been re-phrased as such. |  | 2021-03-02
20 | Garret | A-29 | Requirements Document | A-29 how small are 'small' weights? Need to define this, otherwise how will it be verified? | JB | The 'weights' of the data that are given by the correlator are determined by the fraction of station data on a particular baseline which is non-zero/unflagged at correlation time. The particular numerical threshold for which 'weight's are considered 'small' is a user determine parameter. The only functionality that this requirement imposes is that it be possible to flag data based on the value of associated correlator weights. We will change the language so that it is clear that this is a user determined parameter. |  | 2021-03-02
21 | Garret | A-30 | Requirements Document | A-30 I assume this means these are automatically-generated flags? | DH,JB | DH: I think Garret is referring to the user-supplied list of flags, which I think could be automatically-generated or not? JB: Right, this requirement specifies that we accept a flag-table, but doesn't say how it is generated, this could be automatically or manually. |  | 2021-03-02
22 | Garret | A-31 | Requirements Document | A-31 are ASCII or CSV the only file types we want to consider? Suggest re-wording this not to be "amenable to human examination" but to be specific about the file types that we want data to be convertible to. | VP | ASCII and CSV are the only file types we are considering at this time. Support for any other file types is TBD, but the emphasis is on a text (not binary format) that can be directly inspected. |  | 2021-03-02
23 | Garret | A-32 | Requirements Document | A-32 should re-word to be more quantifiable. Is just implementing an algorithm ok, or do we want to specify some performance target for that algorithm? | VP | Implementing an algorithm to do this task ought to be enough, as this is an entirely new feature, and its performance cannot be compared to an existing implementation. Any specification of the performance of said algorithm would need a set of requirements to specify the exact data-set and quantities to be solved for, in order that a validation test could be made. |  | 2021-03-02
24 | Garret | A-33 | Requirements Document | A-33 this also seems a bit vague, while the comment below offers more detail. "ability to correct either phase or amplitude or both" sounds like a separate requirement. Does simply "applying complex bandpass correction" meet the need? How do we know this is successful? | JB | The application of both an amplitude and phase correction is equivalent to fully 'complex bandpass correction', so the statement that HOPS4 will support complex bandpass correction is sufficient. This is a new feature for HOPS4 which will be incorporated with an appropriate unit/integration test to ensure it is functional. |  | 2021-03-02
25 | Garret | A-35 | Requirements Document | A-35 should the HOPS4 data objects for which we want python wrappers be specified? All of them? Some? Just the new data objects? | VP | At the moment the only requirement is that the data containers in HOPS4 have an appropriate python interface. The exact implementation of that interface and the objects which it covers is TBD and to be part of the specification. |  | 2021-03-02
26 | Garret | D-38 | Requirements Document | D-38 vague requirement. Which more sophisticated tools? How do we determine what qualifies as 'more sophisticated'? | VP | "More sophisticated tools" is determined by the HOPS4 development team, and is relative to HOPS3. The criteria for these dev tools is that they be appropriate for performance analysis like Valgrind for memory leaks/profiling, and/or a built-in timer for evaluating the speed of specific sections of code. The exact dev tools to be used is TBD. |  | 2021-03-02
27 | Garret | D-39 | Requirements Document | D-39 what is the impact of this requirement? How is it tested? This sounds more like a high level requirement that is fulfilled by lower level module or subsystem requirements | DH | DH: it's a desire (spectral-line VLBI, with the option to de-scope if necessary). |  | 2021-03-02
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42